## Sheet1
BMI Calculator Project Schedule
Bogazici University
| Project Lead: |  |  | Cem Sanal
| Project Start Date: |  |  | 2016-09-25
| Display Week: |  |  | 1
|  |  | Tags: | Research
Practice
Question
WBS | Task | Type 1 | Prede cessor | Start | End | Working Hours | % Done
1 | [Task Category]
1.1 | Adaptation for Github | Research, Practice |  | 2016-09-25 | 2016-09-25 | 6 | 100%
1.2 | Adaptation for Git | Research, Practice |  | 2016-09-25 | 2016-09-25 | 3 | 100%
1.3 | Setting up the Web Service | Research, Practice |  | 2016-09-26 | 2016-09-26 | 3 | 100%
1.4 | Requirements Elicitation | Research, Question |  | 2016-09-26 | - | 10 | 90%
1.5 | Creating Visual Mockups | Research, Practice, Question |  | 2016-10-01 | - | 9 | 70%
1.6 | Deciding Frameworks to use | Research, Practice, Question |  | 2016-10-01 | 2016-10-12 | 5 | 80%
1.7 | GitHub Documentation | Practice |  | 2016-09-25 | - | 10 | 10%
1.8 | Registered user Use Case | Practice, Question |  | 2016-10-09 | - | 3 | 80%
1.9 | Finding the working and full Spring IDE. | Practice |  | 2016-10-14 | 2016-10-14 | 2 | 100%
1.10 | Enabling Jquery and Bootstrap inside Java Spring MVC project |  |  | 2016-10-14 | 2016-10-14 | 3 | 100%
1.11 | Learning Java Spring with MVC | Practice, Research |  | 2016-10-14 | - | 50 | 70%
| Total |  |  |  |  | 104
Note on A9: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to control the numbering, but the formulas are different for different levels.
Note on B9: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C9: Type Enter the types with comas.
Note on D9: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version includes template rows that allow you to automatically calculate the Start Date based on the Predecessor.
Note on E9: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G9: Work Hours Counts the number of work hours.
Note on H9: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I9: Work Days Counts the number of work hours.
Note on B11: CEM: Learning Markup language and to use Github
Note on B12: CEM: Command line for GitHub
Note on B15: CEM: Creating Mockups with the help of GIMP and paint
Note on B16: CEM: Researching on Bootstrap and Java Spring Frameworks to understand whether or not they are usable.